## Slide 1: ITERATION 2 METRICS

## Slide 2: Schedule Metrics

## Slide 3: Schedule Metrics
Iteration | Estimated Days | Actual Days | Schedule Metric Index | What can be improved
1 | 4 | 4 | 1.00 | -
2 | 13 | 14 | 0.93 | Allocate debugging time after deployment

## Slide 4: Pair Programming Metrics

## Slide 5: Pair Programming Metrics
Functionality | Coders | Estimated Hours | Actual Hours | PP Index | What we can Improve
UI for Login/Logout and Bootstrap | Eva & Yuxuan | 2.0 | 1.8 | 1.13 | 
Login/Logout | Eva & Yuxuan | 5.0 | 5.2 | 0.97 | 
Code Bootstrap (Unzip, Read data files and create SQL tables) | Wu Di & Max | 6.0 | 5.7 | 1.06 | 
Code Bootstrap (Validate data files, connect to database, insert into tables, drop tables) | Wu Di & Max | 6.0 | 11.4 | 0.52 | 
Integrate functionalities | Wu Di & Max | 2.0 | 0.8 | 2.50 | 
Debugging Bootstrap | Wu Di & Max | 6.0 | 6.3 | 0.95 | 
Debugging Login/Logout | Eva & Yuxuan | 3.0 | 2.0 | 1.54 | 

## Slide 6: Pair Programming Metrics
Functionality | Coders | Estimated Hours | Actual Hours | PP Index | What we can Improve
UI for Login/Logout and Bootstrap | Eva & Yuxuan | 2.0 | 1.8 | 1.13 | 
Login/Logout | Eva & Yuxuan | 5.0 | 5.2 | 0.97 | 
Code Bootstrap (Unzip, Read data files and create SQL tables) | Wu Di & Max | 6.0 | 5.7 | 1.06 | 
Code Bootstrap (Validate data files, connect to database, insert into tables, drop tables) | Wu Di & Max | 6.0 | 11.4 | 0.52 | 
Integrate functionalities | Wu Di & Max | 2.0 | 0.8 | 2.50 | Estimate Integration time better. (Lower)
Debugging Bootstrap | Wu Di & Max | 6.0 | 6.3 | 0.95 | 
Debugging Login/Logout | Eva & Yuxuan | 3.0 | 2.0 | 1.54 | Allocate debugging time better according to difficulty of functionality

## Slide 7: Bug Metrics
Functionality | Bug Details | Category
Login/Logout | Separate User and Admin Login pages. Need to Integrate them. | Low Impact (1 point)
Bootstrap | Takes longer than 15 minutes to upload and validate data | High Impact (5 points)
Overall Score = 6 < 10
Therefore, Errors should be debugged in planned debugging time