## PPM
PP Metric
Iteration | Task # | Task name | Planned Hour | Actual Hour | PPM Score | Reason for socre out of range | Coder1 | Coder2 | Result | Reason | Reason for adhoc | action plan
2 | 1 | UI for Login/Logout and Bootstrap | 2 | 1.77 | 1.13 |  | YX | EVA | all match
2 | 2 | Login/Logout | 5 | 5.17 | 0.97 |  | YX | EVA | all match
2 | 3 | Code Bootstrap (Unzip, Read data files and create SQL tables) | 6 | 5.67 | 1.06 |  | MAX | WD | all match
2 | 4 | Code Bootstrap (Validate data files, connect to database, insert into tables, drop tables) | 6 | 11.43 | 0.52 | over-estimtated the coding time | MAX | WD | one early | wantted to use another way to use another way, but failed so keep the first commit without another commit
2 | 5 | Integrate functionalities | 2 | 0.8 | 2.5 |  | YX | EVA | all match |  |  | 1. Need to re-estimate the tasks in the coming iteration(s) ) and update the schedule document. 2. Review possible pairing & estimation issues.
2 | 6 | Debugging Login/Logout | 3 | 1.95 | 1.54 |  | MAX | WD | all match |  |  | 1. Need to re-estimate the tasks in the coming iteration(s) ) and update the schedule document. 2. Review possible pairing & estimation issues.
2 | 7 | Debugging bootstrap | 6 | 6.3 | 0.95 |  | YX | EVA | all match
3 | 8 | Optimize functionalities from Iteration 2 | 1 | 0.98 | 1.0204 |  | MAX | YX | all match
3 | 9 | View the density for each semantic for any specific time | 6 | 8.83 | 0.68 |  | MAX | EVA | all match
3 | 10 | Generate heat map according to the density | 15 | 6.02 | 2.49 | over-estimtated the coding time | MAX | EVA | one early |  |  | 1. Need to re-estimate the tasks in the coming iteration(s) ) and update the schedule document. 2. Review possible pairing & estimation issues.
3 | 11 | top-k-companions | 4 | 7.47 | 0.54 |  | AAYUSH | WD | all match
3 | 12 | Breakdown by year and gender | 6 | 10.12 | 0.59 |  | AAYUSH | WD | all match
3 | 13 | Top-k next places | 2 | 2.78 | 0.72 |  | AAYUSH | WD | all match
3 | 14 | Top-k popular places | 2 | 2.08 | 0.96 |  | AAYUSH | WD | all match |  | Requirement for project changed:validating the semantic place
3 | 15 | Change in project requirement | 0.5 | 0.43 | 1.15 |  | EVA | MAX | all match
3 | 16 | Integrate heat map and basic location report | 1 | 0.57 | 1.76 |  | AAYUSH | EVA | match |  | nothing changed | 1. Need to re-estimate the tasks in the coming iteration and update the schedule document. 2. Review possible pairing & estimation issues.
3 | 17 | Debug basic location report | 4 | 4.27 | 0.94 |  | AAYUSH | EVA | All match
3 | 18 | Debug heatmap functionality | 6 | 0.8 | 7.5 |  | MAX | EVA | all match |  | Iteration extended, while requirement for milestone in next iteration must be done in advance
3 | 19 | Prepare UI for HT | 1 | 2.05 | 0.49 | Forgot checking navi bar feasibility at the first time, so we have another time to log | MAX | EVA | all match |  |  | 1. Need to re-estimate the tasks in the coming iteration and update the schedule document. 2. Review possible pairing & estimation issues.
| 20 | Prepare bootstrap for Heuristic | 1 | 1.03 | 0.97 |  | MAX | EVA
3 | 21 | Deployment for Heuristic | 1 | 2.2 | 0.45 | war file got unknown problem at the first time, the problem fixed one hours later | AAYUSH | EVA | not match | nothing changed in code
3 | 22 | Deployment | 1 | 1.68 | 0.59 |  | MAX | EVA | All match |  | Put deployment as nun-coding task at the beginning
4 | 23 | Administrative Updating Data | 5 | 5.08 | 0.98 |  | MAX | EVA | All match
4 | 24 | Web Service & JSON (less group detection and reports) | 8 | 7.8 | 1.02 |  | MAX | EVA | All match
4 | 25 | AGD(Check for tricky case, Output according to requirement) | 8 | 8.33 | 0.96 |  | YUXUAN | AAYUSH | All match
4 | 26 | AGD(Basic UI, SQL queries, identify groups) | 7 | 7.82 | 0.9 |  | YUXUAN | AAYUSH | All match
4 | 27 | Integrate functionalities | 1 | 0.85 | 1.18 |  | MAX | AAYUSH | All match
4 | 28 | Deployment | 3 | 2.88 | 1.04 |  | YUXUAN | EVA | All match
4 | 29 | Debug Administrative Updating data and JSON | 3 | 2.05 | 1.46 |  | MAX | EVA | All match
4 | 30 | Debug Automatic Group Identification | 5 | 6.07 | 0.82 |  | YUXUAN | AAYUSH | All match
4 | 31 | Debug Functionalities | 4 | 4.02 | 1 |  | YUXUAN | EVA | All match
4 | 32 | Re-deployment | 2 | 1.63 | 1.22 |  | MAX | EVA | not match | lib closed after start the timer and press wrongly with "stop" instead of "undo"
5 | 33 | Modify Bootstrap according to requirement | 2 | 1.82 | 1.1 |  | MAX | AAYUSH | all match
5 | 34 | Implent changes from Heurisitic | 4 | 3.57 | 1.12 |  | MAX | AAYUSH | all match
5 | 35 | GALR (Top K popular places for groups) | 6 | 4.13 | 1.45 |  | YUXUAN | EVA | all match
5 | 36 | JSON for groups | 4 | 3.73 | 1.07 |  | MAX | AAYUSH | all match
5 | 37 | GALR(Top-k next places for groups) | 8 | 7.2 | 1.11 |  | YUXUAN | EVA | all match
5 | 38 | Deploy on openshift | 2 | 1.53 | 1.3 |  | MAX | AAYUSH | all match
5 | 39 | Integration of functionality | 1 | 0.82 | 1.22 |  | MAX | AAYUSH | all match
5 | 40 | Debug functionities | 4 | 3.23 | 1.24 |  | MAX | AAYUSH | all match
5 | 41 | Implement changes from Heuristic | 4 | 3.6 | 1.11 |  | MAX | AAYUSH | all match
5 | 42 | Debug for JSON | 2 | 1.93 | 1.03 |  | YUXUAN | EVA | all match
5 | 43 | Debug GALR functionality | 4 | 4.27 | 0.94 |  | YUXUAN | EVA | all match
5 | 44 | Re-deployment | 1 | 0.45 | 2.22 |  | YUXUAN | EVA | all match
6 | 45 | Generate Javadocs(Bootstrap,admin update) | 4 | 3.92 | 1.02 |  | YUXUAN | WD | all match
6 | 46 | Generate Javadocs(Group Aware Location Report) | 4 | 3.62 | 1.11 |  | YUXUAN | WD | all match
6 | 47 | Generate Javadocs(Automatic Group Detection) | 2 | 1.93 | 1.03 |  | YUXUAN | WD | all match
6 | 48 | Generate Javadocs(Basic Location Report) | 6 | 4.65 | 1.29 |  | AAYUSH | WD | all match
6 | 49 | Generate Javadocs(Heatmap) | 1.5 | 1.78 | 0.84 |  | YUXUAN | WD | all match
6 | 50 | Improve accuracy of app from UAT | 6 | 6.48 | 0.93 |  | YUXUAN | WD | early
6 | 51 | Improve UI from UAT | 6 | 6.22 | 0.97 |  | AAYUSH | EVA | all match
6 | 52 | Initial Deployment | 1 | 0.7 | 1.43 |  | YUXUAN | EVA | all match
6 | 53 | Integration of functionality | 1.5 | 1.32 | 1.14 |  | YUXUAN | WD | all match
6 | 54 | Debug changes from UAT | 4 | 3.17 | 1.26 |  | AAYUSH | WD | all match
6 | 55 | Debug Functionalities | 3 | 2.77 | 1.08 |  | YUXUAN | WD | all match
6 | 56 | Debug UI changes | 3 | 2.62 | 1.15 |  | AAYUSH | EVA | all match
6 | 57 | Deployment after Debug | 1 | 0.88 | 1.13 |  | YUXUAN | WD
7 | 58 | Update UI | 4 | 3.2 | 1.25 |  | YUXUAN | WD
7 | 59 | Updating of javadocs | 1 | 0.78 | 1.28 |  | YUXUAN | WD
7 | 60 | Update json from UAT | 3 | 3.65 | 0.82 |  | MAX | EVA
7 | 61 | Update Bootstrap | 3 | 2.53 | 1.18 |  | MAX | AAYUSH
7 | 62 | Deploy on openshift | 1 | 0.88 | 1.13 |  | YUXUAN | WD
7 | 63 | Debug json | 1 | 0.88 | 1.13 |  | MAX | AAYUSH
7 | 64 | Debug UI errors | 2 | 3.17 | 0.63 |  | YUXUAN | WU
7 | 65 | Debug Functionalities
7 | 66 | Re-deployment

## ScheduleM
Schedule Metric
Iteraton | Plan | Actual | SM | action plan
1 | 4 | 4 | 1 | on track, we have 7 buffer days
2 | 13 | 14 | 0.93 | the estimates are fairly accurate and we are roughly on track, deduct 1 day from buffer.
3 | 14 | 19 | 0.74 | need to re-estimate the tasks for the future iteration, deduct 5 days from buffer.
4 | 8 | 8 | 1 | on track, we have 1 buffer day
5 | 6 | 6 | 1 | on track, we have 1 buffer day

## Bug Metric
Bug Metric |  |  |  |  | Total Score | 0
Iteration | Functionality | Bug Details | Category | Score | Solve | Debuging Time | Debugged by | Total Bug Score | ScoreCount | action plan
2 | Login/Logout | Separate User and Admin Login pages. Need to Integrate them. | Low Impact | 1 | Y | 2014-09-24 | Yuxuan&Eva | 7 | 0 | Use the planned debugging time.
2 | Login/Logout | Page is protected for bootstrap result | Low Impact | 1 | Y | 2014-09-24 | Yuxuan&Eva |  | 0
2 | Bootstrap | Takes longer than 15 minutes to upload and validate data | High Impact | 5 | Y | 2014-9-24 to 2014-9-26 | Max&Wudi |  | 0
3 | Deployment | Data cannot be loaded into the Openshift database. | Critical Impact | 10 | Y | 2014-09-29 | Max&Yuxuan | 29 | 0 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
3 | HeatMap&BasicLocationReport | No errorMsg when there is no data in the database | Low Impact | 1 | Y | 2014-10-17 | Aayush&Eva |  | 0 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
3 | BasicLocationReport | Multiple user can use the functionality at the same time | Critical Impact | 10 | Y | 2014-10-17 | Aayush&Eva |  | 0
3 | BasicLocationReport(BreakDown) | Cells pushing up and dislocation | Low Impact | 1 | Y | 2014-10-17 | Aayush&Eva |  | 0 | Use the planned debugging time.
3 | BasicLocationReport(BreakDown) | Header missing | Low Impact | 1 | Y | 2014-10-17 | Aayush&Eva |  | 0
3 | BasicLocationReport(BreakDown) | Error page come out when choosing same category for same choices | High Impact | 5 | Y | 2014-10-17 | Aayush&Eva |  | 0
3 | BasicLocationReport(TopKCompaion) | No errorMsg when user key in invalid macAddress | Low Impact | 1 | Y | 2014-10-17 | Aayush&Eva |  | 0
4 | BasicLocationReport(TopKCompaion) | Calculate the people come to the location before the specific person | Low Impact | 1 | Y | 2014-10-25 | Yuxuan&Eva | 8 | 0 | Use the planned debugging time.
4 | JSON(Breakdown) | show error message the order is invalid | Low Impact | 1 | Y | 2014-10-23 to 2014-10-24 | Max&Eva |  | 0
4 | Administrative Updating data | show error message when no file has been choosed | Low Impact | 1 | Y | 2014-10-23 to 2014-10-24 | Max&Eva |  | 0
4 | Automatic Group Identification | The process cannot handle the bigger size of data | Critical Impact | 5 | Y | 2014-10-23 to 2014-10-24 | Yuxuan&Aayush |  | 0
5 | HeatMap&BasicLocationReport&Login | The input box cannot show the input history after user click "submit" | Low Impact | 1 | Y | 2014-10-31 | Max&Aayush | 3 | 0 | Use the planned debugging time.
5 | basicLocationReport&heatmap&AGD&GALR | The empty shows "null" instead of empty, and the message is missing when there is no data at the choosen time | Low Impact | 1 | Y | 2014-10-31 | Yuxuan&Eva |  | 0
5 | json(groups) | The is no error status and wrong error message. | Low Impact | 1 | Y | 2014-10-31 | Max&Aayush |  | 0
6 | UI | Admin welcome page does not immediately show admin bootstrap functionality | low impact | 1 | Y | 2014-11-08 | Eva and Aayush | 8 | 0 | Use the planned debugging time.
6 | UI | "hi" printed out on Top k companions page above results table | low impact | 1 | Y | 2014-11-08 | Eva and Aayush |  | 0
6 | UI | UI does not fit test resolution | low impact | 1 | Y | 2014-11-08 | Eva and Aayush |  | 0
6 | Top k next places | Top k next places missing out on corner cases | Critical impact | 5 | Y | 2014-11-08 | Yuxuan and Wudi |  | 0
7 | basic location report breakdown | json not printing out all results | Critical Impact | 5 | Y | 2014-11-15 | Aayush and Max | 9 | 0 | Use the planned debugging time.
7 | UI | unable to pick second and third option after first attempt of the form | low impact | 1 | Y | 2014-11-15 | Yu Xuan and Wu Di |  | 0
7 | AGI | Results not sorted according to macAddress | low impact | 1 | Y | 2014-11-16 | Yu Xuan and Wudi |  | 0
7 | UI | admin url should end with admin not adminDisplay.jsp | low impact | 1 | Y | 2014-11-16 |  |  | 0
7 | UI | % column not displayed in whole numbers | low impact | 1 | Y | 2014-11-16 | Yu Xuan and Wudi |  | 0
[7 empty] | Total Bug Count: | 64

## Mitigation Plan
Risk Mitigation
Bug Mitigation Plan
Severity | Description | Points in Iteration | Action
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. | Points=<5 | Fix during buffer time only. If there is no buffer time, fix in planned debugging time
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working. | 5<Points<10 | Use the planned debugging time.
Critical Impact(10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue. | Points>=10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Schedule Risk Mitigation Plan
Metrics: estimated/actual time
Score(%) | Action
SM < 50 | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 50 < SM < 90 and seriously consider dropping tasks.
50 < SM <= 90 | 1.Re-estimate the tasks for the future iterations.
2.Deduct the number of days behind schedule from buffer days.
3.If there is no more buffer day, decide the functionalities to drop.
90 < SM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1.Add/Deduct the number of days behind schedule from buffer days.
2.If there is no more buffer day, decide the functionalities to drop
110 < SM <= 150 | Gross over-estimated the effort required.
1.Re-estimate the tasks for the future iterations.
2.Add the number of days gained to buffer days.
150 < SM | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 110 < SM < 150
Pair Programming Mitigation Plan
Score(%) | Action
PPM < 50 | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
2.Review possible pairing & estimation issues.
50 < PPM <= 150 | No action required.
150 < PPM | 1.Re-estimate the tasks in the coming iteration(s) ) and update the schedule document.
2.Review possible pairing & estimation issues.