## Slide 1: Final Presentation
Aayush Garg
Eva Tan
Max Chua
Wu Di Yuan Yu Xuan

## Slide 2
1. Schedule
2. Metrics
3. Subversion Log
4. Others
SCOPE:

## Slide 3
Actual Vs Planned
Iteration 2
Iteration 1
Iteration 3
Iteration 2
Iteration 1
Iteration 3
10-Sep
13-Sep
28-Sep
17-Oct
10-Sep
13-Sep
27-Sep
12-Oct
Planned
Actual
Notes: Planned vs Actual

## Slide 4
Actual Vs Planned
Iteration 5
Iteration 4
Iteration 6
Iteration 5
Iteration 4
Iteration 6
18-Oct
25-Oct
26-Oct
16-Oct
18-Oct
25-Oct
31-Oct
9-Oct
Planned
Actual
26-Oct
1-Nov
11-Oct
16-Oct
31-Oct
9-Oct
1-Nov
11-Oct
Iteration 7
Iteration 7
Notes: Planned vs Actual

## Slide 5
No dropping/addition of functionalities
Framework: Model View Controller(MVC)
External Libraries:
GSON
IS203-JWT
JSON-SMART
NIMBUS-JOSE-JWT
MYSQL-Connector
Commons-FileUpload
Commons-IO
OpenCSV
Functionalities Update
Notes: Planned vs Actual

## Slide 6
Coding Tasks Breakdown
Functionalities | Aayush | Eva | Max | Wu Di | Yu Xuan
Bootstrap |  |  |  |  | 
Admin Update |  |  |  |  | 
Login/Logout |  |  |  |  | 
Basic Location Report |  |  |  |  | 
Heatmap |  |  |  |  | 
Automatic Group Detection |  |  |  |  | 
Group Aware Location Report |  |  |  |  | 
Web Service UI + JSON(-Group JSON) |  |  |  |  | 
Notes: Planned vs Actual

## Slide 7
Coding Tasks Breakdown
Tasks | Aayush | Eva | Max | Wu Di | Yu Xuan
Improve UI from UAT |  |  |  |  | 
Modify bootstrap |  |  |  |  | 
Implement changes from Heuristic |  |  |  |  | 
Group JSON |  |  |  |  | 
Generate javadocs (AGD, bootstrap, admin update, GALR) |  |  |  |  | 
Generate javadocs (BLR) |  |  |  |  | 
Generate javadocs (heatmap) |  |  |  |  | 
Improve accuracy from UAT |  |  |  |  | 
Update bootstrap |  |  |  |  | 
Update UI |  |  |  |  | 
Update JSON |  |  |  |  | 
Update javadocs |  |  |  |  | 
Notes: Planned vs Actual

## Slide 8
Project Manager Schedule
Iteration | Name | Milestone Covered
1, 2 | Aayush | PM Review
3 | Yu Xuan | 2 Supervisor Meetings Heuristic Evaluation
4,5 | Wu Di | Supervisor Meeting
6 | Max Chua | UAT
7 | Eva Tan | Final Presentation
Notes: Planned vs Actual

## Slide 9
Coding Tasks Breakdown
Chart: 
| Aayush | Eva | Max | Wu Di | Yuxuan
Hours Spent (Programming) | 89.68 | 89.42 | 87.98 | 88.07 | 88.02
Column1 | 0.20236 | 0.20177 | 0.19852 | 0.19873 | 0.19861
Member | Coding Hours | % Percentage
Aayush | 89.68 | 20.24
Eva | 89.42 | 20.18
Max | 87.98 | 19.85
Wu Di | 88.07 | 19.87
Yuxuan | 88.02 | 19.86
Average coding hours: 88.634
Notes: Planned vs Actual

## Slide 10
Chart: 
Non-coding Tasks Breakdown
Chart: 
| Aayush | Eva | Max | Wu Di | Yuxuan
Hours Spent (Non-coding) | 47.2 | 50 | 50.5 | 53.8 | 50.5
Column1 | 0.1873 | 0.19841 | 0.2004 | 0.21349 | 0.2004
Member | Non-Coding Hours | % Percentage
Aayush | 47.2 | 18.73
Eva | 50 | 19.84
Max | 50.5 | 20.04
Wu Di | 53.8 | 21.37
Yuxuan | 50.5 | 20.04
Average non-coding hours:
50.40
Notes: Planned vs Actual

## Slide 11
Chart: 
Tasks Breakdown- Total
Chart: 
| Aayush | Eva | Max | Wu Di | Yuxuan
Hours Spent (Total) | 136.88 | 139.42 | 138.48 | 141.87 | 138.52
Member | Total Hours | % Percentage
Aayush | 136.88 | 19.70
Eva | 139.42 | 20.06
Max | 138.48 | 19.92
Wu Di | 141.87 | 20.41
Yuxuan | 138.52 | 19.93
Average hours:
139.034
Notes: Planned vs Actual

## Slide 12
Fair Distribution of Work
Each member took on a role as a Project Manager
Total non-coding hours are generally even
Total coding hours are generally even
Fair share of programming tasks with different level of difficulties

## Slide 13
Schedule Metrics
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7
Score | 1 | 0.93 | 0.74 | 1 | 1 | 1 | 1
Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7
1 | 0.93 | 0.74 | 1 | 1 | 1 | 1

## Slide 14
Problems faced in Iteration2
Reasons:
Overestimated login/logout function
Underestimated time taken to bootstrap
Action Plan:
Re-estimate time taken for each tasks.
Evaluate subsequent tasks in the upcoming iterations.

## Slide 15
Problems faced in Iteration3
Reasons:
Underestimated the amount of time needed to research on how to generate a heatmap.
Json heatmap results were unable to connect to SVG images.
Basic location report was much more complicated than estimated.
Bug Metrics – 29
Action Plan:
Attended heatmap supplementary class.
Read the requirements and discussed more thoroughly in order to better estimate time for coding tasks
Resolve critical bugs before proceeding
Notes: In script mention how you used the metrics to fix problems identified and challenges faced when collecting and using the metrics.

## Slide 16
Bug Metrics
Chart: 
| Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7
Score | 7 | 29 | 8 | 3 | 8 | 9
Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7
7 | 29 | 8 | 3 | 8 | 9

## Slide 17
Bug Metrics
Iteration 3
Unsure of why data was unable to load on to OpenShift
Multiple users overwrote each other’s query,
hence results were not displayed.
Action Plan:
Stop all coding functionalities and resolve bug immediately.
Consulted prof for help.

## Slide 18
Bug Metrics
Challenges | Solutions
Didn’t know if UI errors were considered as bugs | Clarified with prof and added any bug which violated the project requirements in the metrics
Determining the severity of the bugs | Discussed as a group for different point of views

## Slide 19
Chart: 
| UI for Login/Logout and Bootstrap | Login/Logout | Code Bootstrap (Unzip, Read data files and create SQL tables) | Code Bootstrap (Validate data files, connect to database, insert into tables, drop tables) | Integrate functionalities | Debugging Login/Logout | Debugging bootstrap | Optimize functionalities from Iteration 2 | View the density for each semantic for any specific time | Generate heat map according to the density | top-k-companions | Breakdown by year and gender | Top-k next places | Top-k popular places | Change in project requirement | Integrate heat map and basic location report | Debug basic location report | Debug heatmap functionality | Prepare UI for HT | Prepare bootstrap for Heuristic | Deployment for Heuristic | Deployment | Administrative Updating Data | Web Service & JSON (less group detection and reports) | AGD(Check for tricky case, Output according to requirement) | AGD(Basic UI, SQL queries, identify groups) | Integrate functionalities
Series 1 | 1.13 | 0.97 | 1.06 | 0.52 | 2.5 | 1.54 | 0.95 | 1.0204 | 0.68 | 2.49 | 0.54 | 0.59 | 0.72 | 0.96 | 1.15 | 1.76 | 0.94 | 7.5 | 0.49 | 0.97 | 0.45 | 0.59 | 0.98 | 1.02 | 0.96 | 0.9 | 1.18
Pair Programming Metrics

## Slide 20
Pair Programming Metrics
Chart: 
| Deployment | Debug Administrative Updating data and JSON | Debug Automatic Group Identification | Debug Functionalities | Re-deployment | Modify Bootstrap according to requirement | Implent changes from Heurisitic | GALR (Top K popular places for groups) | JSON for groups | GALR(Top-k next places for groups) | Deploy on openshift | Integration of functionality | Debug functionities | Implement changes from Heuristic | Debug for JSON | Debug GALR functionality | Re-deployment | Generate Javadocs(Bootstrap,admin update) | Generate Javadocs(Group Aware Location Report) | Generate Javadocs(Automatic Group Detection) | Generate Javadocs(Basic Location Report) | Generate Javadocs(Heatmap) | Improve accuracy of app from UAT | Improve UI from UAT | Initial Deployment | Integration of functionality | Debug changes from UAT | Debug Functionalities | Debug UI changes | Deployment after Debug | Update UI | Updating of javadocs | Update json from UAT | Update Bootstrap | Deploy on openshift | Debug json | Debug UI errors | Debug Functionalities | Re-deployment
PP score | 1.04 | 1.46 | 0.82 | 1 | 1.22 | 1.1 | 1.12 | 1.45 | 1.07 | 1.11 | 1.3 | 1.22 | 1.24 | 1.11 | 1.03 | 0.94 | 2.22 | 1.02 | 1.11 | 1.03 | 1.29 | 0.84 | 0.93 | 0.97 | 1.43 | 1.14 | 1.26 | 1.08 | 1.15 | 1.13 | 1.25 | 1.28 | 0.82 | 1.18 | 1.13 | 1.13 | 0.63 | 0.79 | 0.63

## Slide 21
Pair Programming Metrics
How we used it?
For better future time estimation for each functional task
Examples:
Iteration 2: Integrate functionalities (2.5)
  Overestimation of the integration, just finished login/logout and bootstrap
  Allocated lesser time for integration in the future iterations.
Iteration 3: Prepare UI for Heuristics (0.49)
  Underestimated complexity of CSS which was a new concept at that time.
  Allocated more time for tasks which require use of new concepts.

## Slide 22
Pair Programming Metrics
Challenges | Solutions
Estimating the time for each task | Understand requirements clearly and infer from previous PP tasks to give more accurate estimations for future tasks
Determining if Deployment was a code task or a miscellaneous task. | Clarified with prof and added deployment as a coding task.

## Slide 23
Subversion Log
CONSISTENT USE!
Notes: Explain that wu di’s commits are high

## Slide 24
Subversion Log
Chart: Number of Commits
| Aayush | Wu Di | Eva | Max | Yu Xuan
Sales | 41 | 55 | 40 | 52 | 47
Notes: Explain that wu di’s commits are high

## Slide 25
Subversion Log
Reason(s) for slightly uneven Subversion log
Initially we didn’t keep track of commits and hence, committed randomly.
Wu Di’s commits were higher due to the role of being a project manager for 2 iterations.
Notes: Planned vs Actual

## Slide 26
Subversion Log
Audit | Iteration 1 | Iteration2 | Iteration 3 | Iteration 4 | Iteration5 | Iteration6 | Iteration7
Early | - | 1 | 1 | - | - | 1 | -
Match | - | 13 | 26 | 21 | 14 | 14 | 9
No Match | - | (+1) | 3(+2) | 1 | - | - | -
Total | - | 15 | 32 | 22 | 14 | 15 | 9
Notes: Planned vs Actual

## Slide 27
Subversion Log
In general, We have used Subversion Correctly!!!
Notes: Planned vs Actual

## Slide 28
Takeaways
“Equal work distribution is healthy for team dynamics”
“Using a schedule contributes to better time management”
“Voicing out disagreements and settling them in a diplomatic way is healthier.”
Notes: Planned vs Actual

## Slide 29
Team Conflicts?
Conflicts due to difference in opinions
 Discuss reasons in detail and then vote to decide
Notes: Planned vs Actual

## Slide 30
“None of us is as smart as all of us”
Notes: Planned vs Actual

## Slide 31
Aayush is from New Delhi (India) but now lives in Singapore
He never ate a snail until the last day of SE Project Submission.
Aayush
Notes: Planned vs Actual

## Slide 32
Eva
Eva dyed her hair for the first time due to stress from SE!
Notes: Planned vs Actual

## Slide 33
Max
Max loves to play Dota.
You will find him in the library EVERYDAY (and night)!
Notes: Planned vs Actual

## Slide 34
Wu Di
Wu Di loves to go shopping!
She is a Taekwondo Instructor and holds a black belt!!! (BEWARE)
The monster is scared of her
Notes: Planned vs Actual

## Slide 35
Yuxuan
Yuxuan(Goddess) is very good at coding and she loves Tea Party. 
She takes at least 6 modules every semester!!!!
Notes: Planned vs Actual

## Slide 36
Thank You!!!!
Notes: Planned vs Actual